## Summary
Issue log summary (updates automatically when Status / Priority are changed)
Status | All | High | Medium | Low
Resolved (business confirmed)
Handled in model
Open - business
Open - ERP team
Open - verify with full data
Assumed - please confirm
Total
Check: total equals number of issues
Open by owner | Open items
Business (you)
ERP team
Data team

## Issue Log
ID | Area | Source file | Issue found | Evidence | Impact if not handled | How the model handles it | Status | Answer / resolution | Priority | Owner
D-001 | Scope | All sample files | Sample files cover Apr-Sep 2026, not from Apr 2025 as planned | Sales, transfers, PO, inventory samples all start 1-Apr-2026 | Forecasting needs a full year incl. festive season | Prototype period set to 1-Apr-2025..15-Sep-2026 | Resolved (business confirmed) | Samples only; full ~1.5-year data will be provided | High | Business (you)
D-002 | Scope | All sources | Full 1.5-year data pull not yet received for any source | Only samples loaded so far | Nothing can be loaded for real yet | Loaders will be built against the sample layouts | Open - business |  | High | Business (you)
D-003 | Scope | Return files | Return files run past the 15-Sep cut-off | 133 retail return rows and 40 domestic return rows dated 16-22 Sep | Returns counted without their matching sales period | Cut-off stored as a setting (meta.pipeline_setting); rows after it excluded at staging | Resolved (business confirmed) | Use data only up to 15-Sep-2026 | Medium | Data team
D-004 | Scope | Inventory | Inventory history cannot be pulled: only today's snapshot | Business confirmed; ERP has no historical stock report | Stock trends impossible for past dates; each unsaved day is lost | Daily snapshot fact; history approximated by rolling back through movements | Open - ERP team | Start saving the ERP, Blinkit and Instamart stock reports daily into a dated folder | High | ERP team
D-005 | Scope | Blinkit / Instamart | Blinkit return sheet (and Instamart's, if any) not received | Business confirmed returns are in a separate sheet | Quick-commerce returns missing; net sales overstated | Will be registered as a new source when received | Open - business | Will be shared when available | Medium | Business (you)
D-006 | Scope | Franchise / SIS | No sell-out data from franchise and SIS stores | Only sell-in invoices exist in the ERP | Stock AI reads stock that later comes back as demand | Demand for these channels uses net sales after returns until sell-out arrives | Open - business | Business will work out how to extract it | Medium | Business (you)
D-007 | Scope | Blinkit / Instamart | No Blinkit or Instamart invoices found in the ERP for Apr-Sep 2026 | No Kiranakart/Swiggy names in Domestic Sales; no QC channel in Retail Sales; yet Kiranakart appears in returns and Blinkit locations hold ERP stock | Quick-commerce revenue may be missing from ERP-based revenue | Revenue = ERP invoices only; platform sell-out stored separately for demand | Open - business | Partly answered: QC is sale-or-return. Still unclear where QC invoices are raised in the ERP | High | Business (you)
D-008 | Scope | WMS dispatch | Dispatch sample was pasted as text, not shared as a file | Rows pasted in chat, dated Apr 2025 | Cannot test joins (e.g. invoice match rate) until a real export arrives | Model designed from the pasted columns | Open - verify with full data |  | Low | Business (you)
D-009 | Retail sales | Retail Sales | CHANNELNAME is the billing location, not the sales channel | Values like '08 Jaipur Branch', '24 FBA WH - AMD2' | Channel reports would show warehouses instead of channels | Channel from CONTACTNAME; CHANNELNAME used as location | Resolved (business confirmed) | Use CONTACTNAME for channel | High | Data team
D-010 | Retail sales | Retail Sales | Channel unclear for some payment modes (COD, Snapmint, FNP, ICICI bank, Advance) | COD = 3,947 lines / Rs 52.9 lakh; Snapmint 80; FNP 19; ICICI 18; Advance 3 | Channel split wrong on the dashboard | Resolved through CONTACTNAME: COD and Snapmint are all under Shopify_Customer (website) | Resolved (business confirmed) | Use CONTACTNAME | High | Data team
D-011 | Retail sales | Retail Sales | PRODASSESSABLEVALUE INCLUDES GST despite its name; PRODDOCVALUE is the excl-GST value | PRODDOCVALUE + GST = PRODASSESSABLEVALUE on every product line; e.g. MRP 850 - disc 17 = 833 incl GST; 705.93 excl | Retail revenue overstated by the GST amount | Headline value = PRODDOCVALUE; load fails if the relationship stops holding | Resolved (business confirmed) | Headline sales = excluding GST | High | Data team
D-012 | Retail sales | Retail Sales | PRODDOCVALUE is blank on charge lines (SHIPPING R, Gifting) | Only non-product lines fail the GST check | Charge revenue lost if PRODDOCVALUE used blindly | Excl-GST value for these lines = PRODASSESSABLEVALUE minus GST; kept as CHARGE item type | Handled in model |  | Low | Data team
D-013 | Retail sales | Retail Sales | Non-product codes appear as invoice lines | SHIPPING R, carry bags COCB04-06, Gifting, packaging codes | Product sales and SKU counts polluted | Every code kept in dim_product with item_type; SKU analysis uses TRADING only | Handled in model |  | Medium | Data team
D-014 | Retail sales | Retail Sales | Bare contact 'Dileep Essentials Pvt Ltd' on retail invoices | 39 lines, Rs 2 lakh; paid via 'DEPL HYD Store A/c', 'DEPL Jaipur - C-Scheme Exp.' | Mis-classified as a D2C sale | Classified as export through Dileep | Resolved (business confirmed) | All are exports through Dileep | Medium | Data team
D-015 | Retail sales | Retail Sales | Two Nykaa names: 'Nykaa Fashion' (900 lines) and 'Nykaa' (34 lines) | Payment modes 'Prepaid - Nykaa Fashion' and 'Prepaid - Nykaa' | Nykaa split across two channels | Proposed: one channel 'Nykaa' with the two names kept as sub-channels | Assumed - please confirm |  | Low | Business (you)
D-016 | Retail sales | Retail Sales | 144 Jaipur Branch rows have a blank payment mode | All at '08 Jaipur Branch' | Payment-type analysis incomplete | Channel comes from CONTACTNAME, so not blocking | Handled in model |  | Low | ERP team
D-017 | Retail sales | Retail Sales | Almost no returns inside the sales file | Only 19 credit notes in 25,899 lines | Returns under-counted | Returns loaded from the dedicated return registers | Resolved (business confirmed) | Return data sheets provided | High | Data team
D-018 | Retail sales | Retail Sales, WMS | Customer personal data (names, phones, emails, addresses) | Present in Retail Sales and WMS dispatch | Privacy and compliance risk | PII stays only in the restricted raw layer; core and mart hold pincode/city/state only | Handled in model |  | High | Data team
D-019 | Domestic sales | Domestic Sales | CONTACTNAME mixes B2B, franchise, SIS, quick commerce, group exports and employees | 117 distinct accounts in the sample | Sale-or-return stock counted as final revenue | Separate partner types; B2B = final, franchise/SIS/QC = sale-or-return | Open - business | Rules confirmed. Billing names of franchise, SIS and QC partners still to be supplied | High | Business (you)
D-020 | Domestic sales | Domestic Sales | Invoices to Dileep group companies | 54 lines, 15 bills, Rs 21.4 lakh (7.75% of domestic taxable), mostly Dileep Crafts | Related-party sales inflate revenue and distort margin | Partner type GROUP_EXPORT: exports at cost, shown as own channel | Resolved (business confirmed) | Exports go through Dileep, billed cost-to-cost | High | Data team
D-021 | Domestic sales | Domestic Sales | Low unit prices on Dileep Industries and Dileep Jewellery bills | Rs 5-25 per unit, no discount (e.g. 280 units for Rs 1,606) | Could look like data errors | Kept as recorded | Resolved (business confirmed) | These are cost prices | Low | Data team
D-022 | Domestic sales | Domestic Sales | CORRECTION: earlier example (price 1,855.93, discount 1,855.09, taxable 0.84) was an Ayush Baid (employee) line, NOT a Dileep bill | Checked: only 2 Dileep lines have a near-100% discount (Sampling Unit Rs 0.97, Potteries Rs 0.96) | Wrong conclusion about Dileep pricing | Record corrected | Resolved (business confirmed) | Corrected in this log | Low | Data team
D-023 | Domestic sales | Domestic Sales | Lines billed at normal price with a 99-100% discount (near-free) | 106 lines, 60 bills, Rs 63 total: Ayush Baid 42, Sundry Customer 22, Tanishq/Titan 14, others | Free units counted as sold: demand inflated for Stock AI; B2B sample units counted as B2B sales | Proposed: flag lines with >=99% discount as 'free / sample issue' and exclude them from demand | Open - business | Are these samples / free issues? | High | Business (you)
D-024 | Domestic sales | Domestic Sales | 'Sundry Customer' is a catch-all account | 171 lines, 21 bills, Rs 4,960 taxable; products incl. cake stand, paper bags, tissue, gift cards | Default rule would treat it as an EMPLOYEE (not on business list) | Held as UNCLASSIFIED until answered | Open - business | What is Sundry Customer (walk-in / cash B2B / misc)? | Medium | Business (you)
D-025 | Domestic sales | Domestic Sales | 209 lines have a blank Taxable value | Mostly carry bags (COCB04-11); 146 on Sundry Customer; Net Amount is present on all of them | Revenue lost for these lines if Taxable used blindly | Proposed: Taxable = Net Amount - Total Tax (relationship holds on 100% of other lines), flagged as derived | Handled in model |  | Medium | Data team
D-026 | Domestic sales | Domestic Sales | Net Amount INCLUDES GST | Taxable + Total Tax = Net Amount on 100% of 5,042 lines | Revenue overstated if Net Amount used | Headline value = Taxable | Resolved (business confirmed) | Headline sales = excluding GST | High | Data team
D-027 | Domestic sales | Domestic Sales | Direct export rows to Singapore, although exports are said to go through Dileep | 2 lines to 'Hindustan Exports', Rs 1 each | Unclear classification | Held as EXPORT_CUSTOMER; Rs 1 lines also fall under the near-free issue | Open - business | Are these samples to an exporter? | Low | Business (you)
D-028 | Domestic sales | Domestic Sales | Person names are employees taking exhibition stock | e.g. Ayush Baid, Riya Sharma | Internal movement counted as B2B sales | Unlisted names = EMPLOYEE by rule; each load reports names classified this way | Resolved (business confirmed) | Any person's name is an employee; no list needed | High | Data team
D-029 | Returns | Retail Sales Return | FBA-named contacts in retail returns | e.g. 'Dileep Essentials Pvt Ltd FBA DED4' | Could be mistaken for internal transfers | Genuine customer returns, received at that FBA warehouse | Resolved (business confirmed) | Customer returns going back to FBA | Medium | Data team
D-030 | Returns | Domestic Sale Return | Person names in domestic returns | e.g. Riya Sharma-Customer, Ayush Baid | Counted as B2B returns | EMPLOYEE by rule; excluded from return-rate metrics | Resolved (business confirmed) | Employees returning exhibition stock | Medium | Data team
D-031 | Returns | Domestic Sale Return | Kiranakart Technologies (Blinkit) appears in domestic returns | Returns found in the domestic return register | Could look misplaced | Unsold stock back from a sale-or-return partner | Resolved (business confirmed) | Blinkit returns unsold stock | Medium | Data team
D-032 | Returns | Domestic Sale Return | Return date field holds several dates joined by ';' | CORRECTED: first read as the same date repeated. Loader found they can DIFFER (437 rows in FY25-26, e.g. '22/11/2024;22/01/2025'); see the goods-receipt issue below | Dates fail to parse or pick the wrong day | Raw keeps the text unchanged; handled with the goods-receipt issue | Handled in model |  | Medium | Data team
D-033 | Returns | Return files | Return date column name differs by file | Retail: RETURNDATE; Domestic: RTNFROMCUSTDT | Wrong column picked | Mapped explicitly per source | Handled in model |  | Low | Data team
D-034 | Returns | Retail Sales Return | ~7% of retail returns don't match a sale in the sample | 2,875 of 3,089 bills matched | Returns without their original sale | Expected (sales before Apr 2026); re-check on full data | Open - verify with full data |  | Low | Data team
D-035 | Returns | Retail Sales Return | Shipping-charge reversal lines in returns | 287 rows with PRODNUM 'SHIPPING R' | Returned 'units' of a non-product | CHARGE item type; excluded from product returns | Handled in model |  | Low | Data team
D-036 | Returns | Domestic Sale Return | Domestic returns have no clear link to the original invoice | BILLNUM here is the credit note; RTNFROMCUST is the goods receipt | Cannot compute return rate per original B2B invoice | Original bill kept nullable | Open - ERP team | Is the original invoice number stored anywhere in this report? | Low | ERP team
D-037 | Returns | WMS, Returns | RTO (failed delivery) vs customer return after delivery | RTO seen in WMS status; customer returns in return registers | Returns mixed or missed | Both kept, as separate events | Resolved (business confirmed) | Return registers provided | Medium | Data team
D-038 | Stock transfers | Stock Transfer, Inward | Sending / receiving location only encoded in the document number prefix | Prefixes JPR/, THA/, HYD, BAG/, AMD ... ; no location column | Stock movements assigned to the wrong place when a new prefix appears | Interim prefix-to-location table (ref.document_prefix_location) | Open - ERP team | Add a branch / location column to transfer and return exports | High | ERP team
D-039 | Stock transfers | Stock Transfer, Inward | Outward stock never received | 31 of 622 outward documents wholly unreceived = 2,311 units (233 from Jun, 34 from May). CORRECTED total counting SKU lines, incl. partly received documents: 2,794 units in transit (built warehouse, verified independently) | Stock can disappear between locations | In-transit view in mart; age of unreceived transfers reported | Open - ERP team | Why are May/June transfers still unreceived? Are FBA receipts recorded in the ERP? | Medium | ERP team
D-040 | Stock transfers | Stock Transfer Inward | Same document + SKU appears twice | 2 duplicate DOCNUM + PRODNUM pairs | Real lines rejected as duplicates | Line-occurrence counter in the key | Handled in model |  | Low | Data team
D-041 | Stock transfers | Stock Transfer | Outward quantities are negative | All outward PRODTRANSQTY < 0 | Signs double-flipped in sums | Stored positive with a direction column | Handled in model |  | Low | Data team
D-042 | Stock transfers | Stock Transfer, Inward | Product hierarchy fields empty | PRODGROUPNAME, PRODBRANDNAME, PRODMODEL, DEPARTMENTNAME 100% blank | No category from these files | Product attributes taken from other sources | Handled in model |  | Low | Data team
D-043 | Stock transfers | All files | Same location spelled differently across files | '24 FBA WH - AMD2' vs 'Dileep Essentials Pvt Ltd Ahmedabad FBA AMD2' | Joins by location fail | One location code with every spelling mapped (ref.location_alias) | Handled in model | Mapping to be reviewed line by line (next step) | High | Data team
D-044 | Purchase orders | Pending PO | PO report contains return invoices, not only purchases | Companies and own stores sending stock back raise invoices here | Returns counted as purchases; lead time wrong | Any counterparty not on the factory list = return-inward | Open - business | Rule confirmed; factory list to be supplied | High | Business (you)
D-045 | Purchase orders | Pending PO | Shoppers Stop appears as a PO counterparty | 'Shoppers Stop Limited-Vendor', 356 rows | Customer mistaken for supplier | Return-inward by rule | Resolved (business confirmed) | Returns raise an invoice in the PO list | Medium | Data team
D-046 | Purchase orders | Pending PO | Returned-to-supplier fields rarely filled | Returned Qty / Value on 27 of 1,350 rows | Supplier return rate looks lower than reality | Kept as reported | Handled in model |  | Low | Data team
D-047 | Purchase orders | Pending PO | CORRECTED: one GRN per PO line was assumed; part deliveries list several receipts in ONE cell | Found by the first transform run: 47 PO lines list 155 receipts in GRNNUM (e.g. 'JPR/GRN/199;305;89') with one date and one total quantity. The loader's uniqueness check could not catch it: it is one cell, not several rows | Per-receipt dates and quantities unknown; supplier lead time approximate for those lines | Receipt table = one row per PO line as reported, receipt numbers in a bridge, lines flagged approximate. Nothing split by guesswork | Open - ERP team | Can the ERP export a GRN register (one row per receipt with its own date and quantity)? Gap G-027 | Medium | ERP team
D-048 | Inventory | Inventory report (.xls) | Stock report is a wide pivot, not a table | 38 location blocks of Qty + MRP side by side; 19 header rows | Hard to load; easy to misalign columns | Loader unpivots to SKU x location and checks block headers | Handled in model |  | Medium | Data team
D-049 | Inventory | Inventory report (.xls) | Report includes non-sellable items | Trading 4,020; Packaging 87; Accessory 49; Stores & Consumables 6 | Stock value and SKU counts polluted | Only TRADING items count as SKUs | Resolved (business confirmed) | Only Trading are SKUs | Medium | Data team
D-050 | Inventory | Inventory, Blinkit inventory | Same Blinkit stock reported by the ERP and by Blinkit | '27 Blinkit - Pune P2' (ERP) and 'Pune P2 - Feeder' (Blinkit) | Stock double-counted | Both kept; each location counted once from its system of record | Open - business | Which is the truth for Blinkit locations: ERP or Blinkit's report? | Medium | Business (you)
D-051 | Inventory | Blinkit inventory | Negative 'Net scheduled inventory' values | e.g. -92, -125 | Wrong stock at Blinkit | Stored; excluded from all stock metrics | Open - business | Being confirmed with Blinkit | Medium | Business (you)
D-052 | Inventory | Amazon FBA | Amazon's own FBA inventory report not provided | FBA stock known only from the ERP | ERP and Amazon may disagree (see unreceived FBA transfers) | FBA locations use ERP until an Amazon report is added | Open - business | Can the Amazon FBA inventory report be exported? | Medium | Business (you)
D-053 | Inventory | Inventory report (.xls) | Product category blank in the stock report | Prod Group / Category columns empty | No category on stock views | Category from sales and PO files | Handled in model |  | Low | Data team
D-054 | Product master | Final Master | Which SKUs are currently sold | 472 Continued, 3,548 Discontinued | Stock AI recommends discontinued SKUs | Lifecycle status from Final Master; discontinued excluded from replenishment | Resolved (business confirmed) | Final Master is the list of current SKUs | High | Data team
D-055 | Product master | Final Master | How current the master's status is |  | Stale status = wrong replenishment | Fresh copy with every data pull; changes kept in product history | Resolved (business confirmed) | Updated whenever something changes | Medium | Data team
D-056 | Product master | Final Master | Only Sheet1 is structured | Other sheets: Mastor Jan 2026, MRP to change Lot 1/2 | Working sheets loaded as data | Only Sheet1 loaded | Handled in model |  | Low | Data team
D-057 | WMS dispatch | WMS dispatch | CORRECTION: channel is in 'Site Location', not 'Customer' (earlier misread) | Customer column = placeholder 999999 | Channel from the wrong column | Channel from Site Location | Resolved (business confirmed) | Corrected | Medium | Data team
D-058 | WMS dispatch | WMS dispatch | Which warehouse 'Warehouse' means | Order Serving Location = 'Warehouse' on every row | Fulfilment location unknown | All shipments = Bagru warehouse | Resolved (business confirmed) | B2C only, all from Bagru | Medium | Data team
D-059 | WMS dispatch | WMS dispatch | Several SKUs in one cell with one combined quantity | e.g. 'SWTEA1766 , WDSWA2926' with Delivery Qty 2 | Per-SKU quantities unknown | Bridge table; per-SKU qty from the matching ERP invoice line, else left empty | Open - verify with full data | Invoice match rate to be checked on the full export | Medium | Data team
D-060 | WMS dispatch | WMS dispatch | Long numbers exported in scientific notation | Ext Manifest No '1.60396E+13' | Digits permanently lost; IDs don't match | All IDs loaded as text | Open - ERP team | Export IDs as text or the report as CSV | Medium | ERP team
D-061 | WMS dispatch | WMS dispatch | Dates in month/day order | e.g. 4/14/2025 | Day and month swapped for dates up to the 12th | Date format declared per source | Handled in model |  | High | Data team
D-062 | WMS dispatch | WMS dispatch | Status values in mixed case | 'Shipped', 'delivered', 'RTO Delivered' | Groupings split | Standardised via ref.code_mapping | Handled in model |  | Low | Data team
D-063 | WMS dispatch | WMS dispatch | Placeholder customer contacts | 9999999999, dummy@nykaa.com, 'No Address Provided' | Fake data in customer analysis | PII not used in core | Handled in model |  | Low | Data team
D-064 | Quick commerce | Blinkit sales | Which Blinkit order statuses count as sold | Sample has 8 rows, all DELIVERED | Demand inflated by cancelled orders | Only DELIVERED counted | Resolved (business confirmed) | Delivered = sold | Medium | Data team
D-065 | Quick commerce | Blinkit sales | No store id in the Blinkit sales export | Only supply / customer city | No store-level demand | Grain uses supply city in place of store | Handled in model |  | Low | Data team
D-066 | Quick commerce | Instamart sales | Brand Metrics sheet is marketing data | City-level metrics, not sales lines |  | Not loaded in this phase | Handled in model |  | Low | Data team
D-067 | Locations | Inventory, Transfers | Bagru warehouse naming across files | '08 Jaipur Branch' = Bagru warehouse (confirmed). Bare 'Dileep Essentials Pvt Ltd' is the same place: it is billed at 08 Jaipur Branch and uses the JPR/ transfer prefixes | Bagru stock split across names | All three names mapped to one location, BAGRU_WH | Resolved (business confirmed) | 08 Jaipur Branch = Bagru warehouse | Medium | Data team
D-068 | Locations | All | Head office location | Standalone 'Dileep Essentials Pvt Ltd' / HO |  | HEAD_OFFICE location in Bagru | Resolved (business confirmed) | HO is in Bagru | Low | Data team
D-069 | General | All | Currency and timezone never explicitly confirmed | All data appears Indian (INR, IST) | Wrong if any foreign-currency data exists | INR and IST stored as settings | Assumed - please confirm |  | Low | Business (you)
D-070 | Inventory | Inventory report (.xls) | The stock report has a 'Total' column that is the sum of all locations | Equals the sum of the 37 location columns on 100% of rows | All stock counted twice if loaded as a location | Loader skips the Total block and uses it only to check the unpivot is complete | Handled in model |  | High | Data team
D-071 | Locations | Inventory report (.xls) | 13 ERP locations hold zero stock, incl. 7 stores with no retail invoices | Stores: GK Store, Indiranagar, VR Mall, Infiniti Malad, SIB Bandra, Goa Anjuna, CG Road. Also DEPL Delhi / Lucknow / Mumbai PPOB and FBA BLR5, NAG1, DED5 | Closed locations clutter reports; stock appearing there later goes unnoticed | Proposed inactive; any stock or sale at an inactive location raises a warning | Assumed - please confirm | See 'Open questions' in Reference_Mappings_Draft_v1 | Medium | Business (you)
D-072 | Locations | Stock transfers | 'Dileep Essentials Pvt Ltd Bagru' is a different location from the Bagru warehouse | Uses transfer prefix BAG/ (2 documents); the Bagru warehouse uses JPR/ | Stock moved to / from it assigned to the wrong place | Left unmapped (goes to Unknown) until answered | Open - business | Is it '08 Bagru Popup'? | Medium | Business (you)
D-073 | Locations | Inventory report (.xls) | '08 Essential - DFAL' holds stock but its purpose is unknown | 688 units of 15 SKUs; transfer prefixes IS/DF and RC/DF | Stock counted as sellable when it may not be | Proposed not sellable until confirmed | Open - business | What is DFAL, and is its stock sellable? | Medium | Business (you)
D-074 | Locations | Inventory report (.xls) | Jaipur Meeraki holds stock but has no retail invoices | 145 units; no Retail Sales rows Apr-Sep 2026 | Store type unclear (own / SIS / franchise) | Proposed own store | Open - business | What kind of store is Meeraki? | Low | Business (you)
D-075 | Locations | Retail Sales Return (FY25-26) | Two store names don't match any ERP location | 'Dileep Essentials Pvt Ltd Jaipur Store' (7 returns) and 'Dileep Essentials Pvt Ltd Lucknow' | Returns received at an unknown location | Left unmapped until answered | Open - business | Which locations are these? | Low | Business (you)
D-076 | Retail sales | Retail Sales Return (FY25-26) | Channels seen only in last year's returns | 'Flipkart Website', 'Ellementry International', and Blinkit Mumbai / Pune contacts | Channel list incomplete for FY25-26 | Flipkart and Blinkit mapped (proposed); Ellementry International left unmapped | Open - business | Which channel is 'Ellementry International'? | Low | Business (you)
D-077 | Returns | Domestic Sale Return | One credit note can cover several goods receipts with different dates | RTNFROMCUST lists receipts ('JPR/GIR/3923;5011;5012') and RTNFROMCUSTDT their dates in the same order; e.g. credit note of 29-Oct-2025 for goods received 22-Nov-2024 and 22-Jan-2025 | 'Return date' is ambiguous: sales reversal (credit note date) vs stock back in hand (receipt date) | Credit-note date (BILLDATE) for net sales; receipt dates for stock timing; each receipt stored separately (bridge_return_goods_receipt) | Resolved (business confirmed) | Approved with Target Data Model v2 (1 Oct 2026): rule BR-023 | High | Data team
D-078 | Returns | Domestic Sale Return | Receipt date list shorter than the receipt list on some credit notes | e.g. 3 receipts with 2 dates; 100 receipts in the sample cannot be paired with a date | Wrong receipt dates if paired by position | Unpaired receipts left out of the receipts bridge; the return uses only the dates given | Open - ERP team | Why does the ERP drop a date when several receipts share one credit note? | Low | ERP team
D-079 | Returns | Domestic Sale Return | A return 'reason' column exists but is never filled | Empty on all 5,924 rows | Return reasons unknown, though the ERP can hold them | Reason dimension ready; reasons load as soon as the field is filled | Open - business | Can the team start filling the reason when raising a credit note? Gap G-009 | Medium | Business (you)
D-080 | Inventory | Built warehouse (stock view) | Stock at sale-or-return partners has no opening balance | Blinkit consignment location shows -5,749 units: Kiranakart returned stock in the period that was invoiced to it before the data starts; Blinkit net sales -Rs 2.44 lakh for the same reason | Partner stock understated, even negative, on dashboards | The stock view labels these balances 'LEDGER: no opening balance'; nothing is clamped or hidden | Open - business | Can each franchise, SIS and quick-commerce partner state the stock it held on 1-Apr-2025? Gap G-028 | High | Business (you)
D-081 | Quick commerce | Instamart sales and inventory | Instamart's 'Elle SKU' shows Excel's N/A lookup error where its lookup failed | 4 sales rows, 6 inventory rows | An Excel error was briefly created as a product | Excel error values are treated as 'no SKU': rows go to Unknown and are counted | Handled in model |  | Low | Data team
D-082 | Returns | Domestic Sale Return | Return date column mixes real Excel dates and typed text | ~90% Excel date cells, ~10% typed text 'dd/mm/yyyy;...' | Only one of the two forms parsed | Loader stores Excel dates as ISO text and keeps typed text unchanged; staging parses both | Handled in model |  | Medium | Data team
D-083 | Purchase orders | Pending PO | The PO export's real date is unknown | File name says '12_09' but it has 77 POs opened after 12-Sep, the latest on 24-Sep, and receipts to 24-Sep | PO state recorded against the wrong date; pending-PO view wrong | Loader refuses a PO file whose as-of date is earlier than dates inside it | Open - business | On what date was this PO report exported? Please note the export date for every future PO pull | Medium | Business (you)
D-084 | Scope | Blinkit / Instamart inventory, Final Master, PO | These exports carry no date of their own | File names give month only (e.g. 'sep_26') or an unclear code | Snapshot loaded against the wrong day | Loader requires --as-of for every snapshot, state or master file | Handled in model | When saving these exports, put the full export date in the file name | Medium | Business (you)
D-085 | Inventory | Inventory report (.xls) | 7 locations are selected in the report filter but have no column | Head Office, 08 Repair and Damage, 08 Offline - WH, 07 FBA WH - DED1, 27 FBA WH - ISK3, 08 Jaipur - Mansarovar, 29 FBA WH - BLX9. 13 other zero-stock locations DO get a column | Stock at these locations (e.g. damaged stock) may be missing from the report | Loader compares filter vs columns on every load and records a warning; locations added to the mapping as proposals | Open - ERP team | Why do these 7 have no column? Does Repair and Damage hold stock? | Medium | ERP team
D-086 | Inventory | Inventory report (.xls) | Report ends with a grand-total row | Per-location totals in Indian number format, e.g. '1,12,92,483.18' | Footer loaded as a product row | Every location column must add up to its footer total, and every row to its Total column, or the whole file is rejected | Handled in model |  | Medium | Data team
D-087 | Product master | Final Master | Sheet1 also contains a full copy of stock columns | After Prod Num/Status/Name/Type/Unit come stock blocks laid out like the stock report | Stale stock read as current inventory | Only the 5 product columns are loaded; the stock copy is ignored by design | Handled in model |  | Medium | Data team
D-088 | Quick commerce | Instamart sales, Blinkit inventory | Columns without a header | Instamart: a 0,1,2... row counter; Blinkit: every value '--' | Real data dropped if an unnamed column ever holds some | Dropped only after checking they are exactly a counter / only '--'; otherwise the file is rejected | Handled in model |  | Low | Data team
D-089 | Returns | Pending PO, Domestic Sale Return | Shoppers Stop returns appear on two routes | PO report: 316 return-inward receipt lines (563 units); Domestic Sale Return: 68 credit-note lines (95 units); only 3 pairs match on SKU, quantity and date | If both record the same goods, the stock ledger counts the return twice | No return-inward movements are created until the factory list arrives and this is answered | Open - business | Are these two different return routes, or the same goods recorded twice? | High | Business (you)
D-090 | Domestic sales | Domestic Sale Return (FY25-26) | 'DILEEP ESSENTIALS INC' appears as a return counterparty | 1 row | Unclear whether it is a group export entity | Listed as UNCLASSIFIED so it is never classified by elimination | Open - business | What is Dileep Essentials Inc? | Low | Business (you)
D-091 | Domestic sales | Domestic Sales, PO | Classification by elimination is unsafe until the partner list is complete | Until the franchise / SIS / quick-commerce and factory names arrive, every unlisted company would become an employee (domestic) or a return-inward (PO) | Real revenue silently treated as internal stock | Safety switch partner_list_complete = false: unlisted names stay UNCLASSIFIED until the business confirms the list is complete | Handled in model |  | High | Data team
D-092 | Quick commerce | Domestic Sales / Returns, Stock Transfers | Two possible supply routes to Blinkit | Kiranakart (Blinkit) appears on domestic credit notes, while stock also reaches Blinkit feeder locations by ERP stock transfer | Blinkit stock split across two pools or counted twice | Kept as two locations: Blinkit consignment stock (invoiced) and the Blinkit feeder locations (transferred) | Open - business | Is Blinkit supplied by invoice, by stock transfer, or did it change over time? | Medium | Business (you)
D-093 | Stock transfers | Stock Transfer Inward | Inward prefix 'STK' is shared by two receiving locations | Used for both AMD2 (20 documents) and LKO1 (1) | Receipts assigned to the wrong location | Receiver taken from the linked outward document, not from the prefix | Handled in model |  | Medium | Data team
D-094 | Purchase orders | Pending Purchase Order 25-26 12.22; Pending Purchase Order 26-27 12.09 (2) | Export date of both PO files is unknown ('12.22' and '12.09' in the file names: time or date unclear) | File names end '12.22' and '12.09'; the sheets have no title row (header on row 1). PO Open Date in the 26-27 file runs to 24-Sep-2026. | The PO table keeps each line's latest status, so a wrong as-of date can roll a line's status back | Loader requires --as-of for ERP_PURCHASE_ORDER; PO loading is blocked until the date is given | Open - business | Needs the business and the ERP team to state the export date (and time) of each PO file | High | Business (you)
D-095 | Inventory | ERP stock report (Inventory report) | Stock 'as on 31-03-2025' not yet requested; rule BR-021 ('stock history cannot be re-pulled') is out of date for ERP locations | Business states the ERP can produce the stock report for any past date. BR-021 is ACTIVE in meta_business_rule and is referenced by meta_column_rule and meta_source_note; D-004 also says history cannot be pulled. | No opening balances for the stock ledger; the warehouse would keep a rule that is no longer true for ERP locations | Request the report as on 31-03-2025 and confirm it is CLOSING stock. BR-021 to be retired and replaced (decision pending; rule seeds not edited) | Open - ERP team |  | High | ERP team
D-096 | Quick commerce | Blinkit and Instamart stock reports | Blinkit and Instamart stock at 15-Sep-2026 cannot be re-fetched; only current-day stock is available | Business confirmed: the platforms show only current-day stock | No stock position at the 15-Sep-2026 period end for quick-commerce locations | Known gap recorded in the file manifest (status GAP); no BLINKIT_INVENTORY or INSTAMART_INVENTORY file for the period | Resolved (business confirmed) | Accepted gap | Medium | Business (you)
D-097 | Quick commerce | Blinkit all time sales Data; Instamart sales | Blinkit and Instamart sales history is a manually assembled workbook and cannot be re-fetched month by month | Blinkit: 15 monthly sheets with changing columns and date formats. Instamart: 18 monthly sheets, 4 without a header row, 1 month with rows from the next month. | Files do not match the loader contracts as they are | Keep the original workbooks untouched; load script-cleaned monthly files; every cleaning decision recorded in CLEANING_PLAN.md | Resolved (business confirmed) | Decision: originals untouched; cleaned monthly files loaded; cleaning rules still to be confirmed in CLEANING_PLAN.md | High | Data team
D-098 | Domestic sales | Domestic Sales 01-04-2025 to 31-03-2026; Domestic Sales 01-04-2026 to 15-09-2026 (1) | DOCID is a 19-digit number stored as a number, so its last digits cannot be exact | All 25,863 DOCID values (20,612 + 5,251) are 19 digits and stored as floating-point numbers (about 15-16 digits are exact) | DOCID cannot be used as a reliable key | DOCID is kept in the raw layer only; not used by the warehouse | Open - ERP team | Ask the ERP team for a text export when convenient | Low | ERP team
D-099 | WMS dispatch | Dispatch order report 1 Apr.2025 to 15 Sep.2026 (1) | Dispatch file is .xlsm and Order Date is a real Excel date, but the draft WMS_DISPATCH contract expects text | Loader reads only .xlsx, .xls and .csv; contract status is 'draft' and was built from a pasted column list (Order Date format text_mdy_time) | File cannot be loaded as it is | Contract to be corrected against the real file before loading | Open - business | Ask Operations to export future dispatch reports as CSV with ID columns as text | Medium | Business (you)
D-100 | Purchase orders | Pending Purchase Order 25-26 12.22; Pending Purchase Order 26-27 12.09 (2) | PO reports now have an extra column 'Document Remark' (38 columns; contract has 37) | Both PO files have the 37 contract columns plus Document Remark; the ERP_PURCHASE_ORDER contract requires an exact column set | Loader would reject the PO files until the contract records the new column | Proposed: record Document Remark in the ERP_PURCHASE_ORDER contract (contract update needed) | Assumed - please confirm |  | Medium | Data team
D-101 | Product master | Ellementry Final Mastor - 2026 september updated | The first Final Master copy supplied lacked Sheet1 | First copy (sha256 e7f9ff8b...) had sheets Mastor - Jan 2026, MRP to change Lot 2, MRP to change Lot 1 and no Sheet1 | PRODUCT_MASTER could not be loaded from that copy | Original supplied: Sheet1 starts with Prod Num, Status, Prod Name, Prod Type, Unit (sha256 f3abe9ce...) | Resolved (business confirmed) | Original file supplied | Medium | Business (you)
D-102 | General | Warehouse build (ellementry_dw v2.2) | Warehouse is to run on PostgreSQL 18; it was tested on PostgreSQL 16 | Package tested on 16; production target is 18 | A difference between versions could break a script or a test | To be confirmed by the test run in Phase 2 | Resolved (business confirmed) | Confirmed: 78/78 schema tests (tests/test_schema.sql) and 63/63 pytest (49 loader, 6 seed, 8 transform; 0 skipped) on PostgreSQL 18.6 + Python 3.13.15, 2026-10-16 | Medium | Data team
D-103 | Product master | Ellementry Final Mastor - 2026 september updated | Final Master as-of date not stated in the file | File metadata (docProps/core.xml): modified 2026-09-25T09:22:05Z, created 2026-02-06T11:10:55Z | Loader requires --as-of for PRODUCT_MASTER; a wrong date mis-times SKU status (Continued / Discontinued) | as_of_date 2026-09-25 used in MANIFEST.tsv, assumed from file metadata | Assumed - please confirm |  | Medium | Business (you)
D-104 | General | Warehouse build (ellementry_dw v2.2) | Python 3.13 used instead of the preferred 3.12 | Only Python 3.13.15 is installed on the build PC; .venv created with 3.13. requirements.txt pins only psycopg, openpyxl and xlrd; pandas (>=2.2) installed 3.0.6 and pytest (>=8) installed 9.1.1 | A library or test could behave differently on 3.13 or on unpinned new major versions | After the tests pass: propose pinning requirements.txt to the exact installed versions as a separate commit | Resolved (business confirmed) | Confirmed: 78/78 schema tests (tests/test_schema.sql) and 63/63 pytest (49 loader, 6 seed, 8 transform; 0 skipped) on PostgreSQL 18.6 + Python 3.13.15, 2026-10-16; requirements.txt pinned to the tested versions (commit 3ae9cea) | Medium | Data team
D-105 | Returns | 484681020741.csv (Amazon customer returns report) | Amazon FBA customer returns report found; candidate source that may close gap G-009 (return reasons) | CSV, 12 columns incl. return-date, order-id, sku, asin, reason, detailed-disposition, customer-comments; 3,499 rows, return-date 2025-04-01 to 2026-09-14. G-009 (OPEN) names marketplace return reports as a way to fill return reasons | Return reasons stay unknown for Amazon returns; the free-text customer-comments column may hold personal data | Not a registered source; stored in C:\ellementry_data\full\_UNREGISTERED\AMAZON_CUSTOMER_RETURNS\ and listed in MANIFEST.tsv as UNREGISTERED. Registering it needs a contract and a decision on customer-comments (exclude or restrict) | Open - business |  | Medium | Business (you)
D-106 | Inventory | Blinkit inventory sep 26; Instamart inventory 26 sep 26; Ellementry Final Mastor - 2026 september updated | As-of dates of snapshot / master files assumed from file save times | Blinkit inventory: last saved 2026-09-25T10:08:47Z (15:38 IST); tests/sample_manifest.tsv said 2026-09-26. Instamart inventory: last saved 2026-09-26T06:03:19Z (11:33 IST), matches 2026-09-26. Final Master: last saved 2026-09-25T09:22:05Z; 2026-09-15 in sample_manifest was a placeholder (owner) | Loader requires --as-of; a wrong date places stock or SKU status on the wrong day | MANIFEST.tsv as_of_date: Blinkit inventory 2026-09-25, Instamart inventory 2026-09-26, Final Master 2026-09-25 (stock files show stock at download time) | Assumed - please confirm |  | Medium | Business (you)
D-107 | General | PostgreSQL server (localhost:5432) | A database named ellementry_dw already exists on the server; it belongs to the other model's prototype | ellementry_dw: owner postgres, 14 MB, warehouse schemas plus an 'app' schema (5 tables); prototype roles ellementry_app and ellementry_metrics exist; prototype scripts/setup_warehouse.sh defaults to ellementry_dw | Building our warehouse under the same name would collide with, or overwrite, the prototype's database | Our warehouse database is ellementry_warehouse (PGDATABASE in ~/.bashrc); ellementry_dw left untouched | Resolved (business confirmed) | Decision: keep ellementry_dw for the prototype evaluation; our warehouse = ellementry_warehouse | Medium | Business (you)
D-108 | Retail sales | Retail Sales 01-04-2026 to 15-09-2026 (sample build dw_transform_test) | Control total Rs 4,22,80,208.54 was mislabelled 'retail net sales' in earlier notes | Rs 4,22,80,208.54 = sum(core.fact_sales_line.net_sales_amount) for ERP_RETAIL_SALES = retail INVOICED sales excluding GST, before returns (sample period Apr-Sep 2026). Net of retail returns dated Apr-Sep 2026 = Rs 3,69,30,320.14 | A total labelled 'net' could be read as net of returns and compared wrongly | Label corrected: invoiced sales excl. GST, before returns. Corrected in PRD-001 | Resolved (business confirmed) | Rs 4,22,80,208.54 is retail INVOICED sales excluding GST, before returns (sample period Apr-Sep 2026); net of returns dated Apr-Sep 2026 = Rs 3,69,30,320.14. Corrected in PRD-001 | Medium | Business (you)
Note on A5: Superseded by D-095: the ERP can produce the stock report for any past date

## Legend
Status | Meaning
Resolved (business confirmed) | The business answered; the answer is applied in the model.
Handled in model | A data quirk the model deals with automatically; no business input needed.
Open - business | Waiting on an answer or data from the business.
Open - ERP team | Waiting on a change or answer from the ERP team.
Open - verify with full data | Design is ready; must be re-checked when the full 1.5-year data arrives.
Assumed - please confirm | The model uses a proposed rule until someone confirms or corrects it.
How to update | Change Status and fill 'Answer / resolution' in the Issue Log. Add new issues as new rows with the next D-number. The Summary sheet recalculates.