## Summary
Ellementry data issue log - 30 Oct 2026
| All | High | Medium | Low
Solved | 82 | 22 | 35 | 25
Unsolved | 43 | 8 | 22 | 13
Unsolved by status
Awaiting confirmation | 6
Open - ERP team | 9
Open - business | 25
Parked - Blinkit | 3
Solved: what the issue was and how it was solved (by a business answer, or handled in the warehouse).
Unsolved: what the issue is, the evidence, why it matters, and what is needed to close it.
Replaces Data_Issues_and_Doubts_Log_2026-10-26.xlsx (kept for history). Same IDs; D-122 to D-125 are new.

## Solved
ID | Area | Issue | How it was solved | Solved by | Priority | Owner
D-001 | Scope | Sample files cover Apr-Sep 2026, not from Apr 2025 as planned | Samples only; full ~1.5-year data will be provided | Resolved by the business | High | Business (you)
D-002 | Scope | Full 1.5-year data pull not yet received for any source | 2026-10-22: full exports received (Apr 2025 - Sep 2026) and loaded; reconciled 28/28 against the files. | Resolved by the business | High | Business (you)
D-003 | Scope | Return files run past the 15-Sep cut-off | Use data only up to 15-Sep-2026 | Resolved by the business | Medium | Data team
D-008 | Scope | Dispatch sample was pasted as text, not shared as a file | 2026-10-22: the full dispatch export arrived as a file (.xlsm); contract verified against it. | Resolved by the business | Low | Business (you)
D-009 | Retail sales | CHANNELNAME is the billing location, not the sales channel | Use CONTACTNAME for channel | Resolved by the business | High | Data team
D-010 | Retail sales | Channel unclear for some payment modes (COD, Snapmint, FNP, ICICI bank, Advance) | Use CONTACTNAME | Resolved by the business | High | Data team
D-011 | Retail sales | PRODASSESSABLEVALUE INCLUDES GST despite its name; PRODDOCVALUE is the excl-GST value | Headline sales = excluding GST | Resolved by the business | High | Data team
D-012 | Retail sales | PRODDOCVALUE is blank on charge lines (SHIPPING R, Gifting) | Excl-GST value for these lines = PRODASSESSABLEVALUE minus GST; kept as CHARGE item type | Handled in the warehouse | Low | Data team
D-013 | Retail sales | Non-product codes appear as invoice lines | Every code kept in dim_product with item_type; SKU analysis uses TRADING only | Handled in the warehouse | Medium | Data team
D-014 | Retail sales | Bare contact 'Dileep Essentials Pvt Ltd' on retail invoices | All are exports through Dileep | Resolved by the business | Medium | Data team
D-016 | Retail sales | 144 Jaipur Branch rows have a blank payment mode | Channel comes from CONTACTNAME, so not blocking | Handled in the warehouse | Low | ERP team
D-017 | Retail sales | Almost no returns inside the sales file | Return data sheets provided | Resolved by the business | High | Data team
D-018 | Retail sales | Customer personal data (names, phones, emails, addresses) | PII stays only in the restricted raw layer; core and mart hold pincode/city/state only | Handled in the warehouse | High | Data team
D-020 | Domestic sales | Invoices to Dileep group companies | Exports go through Dileep, billed cost-to-cost | Resolved by the business | High | Data team
D-021 | Domestic sales | Low unit prices on Dileep Industries and Dileep Jewellery bills | These are cost prices | Resolved by the business | Low | Data team
D-022 | Domestic sales | CORRECTION: earlier example (price 1,855.93, discount 1,855.09, taxable 0.84) was an Ayush Baid (employee) line, NOT a Dileep bill | Corrected in this log | Resolved by the business | Low | Data team
D-025 | Domestic sales | 209 lines have a blank Taxable value | Proposed: Taxable = Net Amount - Total Tax (relationship holds on 100% of other lines), flagged as derived | Handled in the warehouse | Medium | Data team
D-026 | Domestic sales | Net Amount INCLUDES GST | Headline sales = excluding GST | Resolved by the business | High | Data team
D-028 | Domestic sales | Person names are employees taking exhibition stock | Any person's name is an employee; no list needed | Resolved by the business | High | Data team
D-029 | Returns | FBA-named contacts in retail returns | Customer returns going back to FBA | Resolved by the business | Medium | Data team
D-030 | Returns | Person names in domestic returns | Employees returning exhibition stock | Resolved by the business | Medium | Data team
D-031 | Returns | Kiranakart Technologies (Blinkit) appears in domestic returns | Blinkit returns unsold stock | Resolved by the business | Medium | Data team
D-032 | Returns | Return date field holds several dates joined by ';' | Raw keeps the text unchanged; handled with the goods-receipt issue | Handled in the warehouse | Medium | Data team
D-033 | Returns | Return date column name differs by file | Mapped explicitly per source | Handled in the warehouse | Low | Data team
D-034 | Returns | ~7% of retail returns don't match a sale in the sample | Re-checked on the full data: returns with no matching sale are for sales before 1 Apr 2025, which are outside the loaded period (retail 1,010 and domestic 1,930 lines). Expected; check return_without_original_sale. | Handled in the warehouse | Low | Data team
D-035 | Returns | Shipping-charge reversal lines in returns | CHARGE item type; excluded from product returns | Handled in the warehouse | Low | Data team
D-037 | Returns | RTO (failed delivery) vs customer return after delivery | Return registers provided | Resolved by the business | Medium | Data team
D-040 | Stock transfers | Same document + SKU appears twice | Line-occurrence counter in the key | Handled in the warehouse | Low | Data team
D-041 | Stock transfers | Outward quantities are negative | Stored positive with a direction column | Handled in the warehouse | Low | Data team
D-042 | Stock transfers | Product hierarchy fields empty | Product attributes taken from other sources | Handled in the warehouse | Low | Data team
D-043 | Stock transfers | Same location spelled differently across files | One location code with every spelling mapped (ref.location_alias). Mapping to be reviewed line by line (next step) | Handled in the warehouse | High | Data team
D-044 | Purchase orders | PO report contains return invoices, not only purchases | Rule BR-031 confirmed (27 Oct 2026): Document Remark 'Purchase' = factory purchase, 'Return' = return-inward. Schema 2.10: open POs and supplier lead time cover purchases only; receipts enter the stock ledger. | Resolved by the business | High | Business (you)
D-045 | Purchase orders | Shoppers Stop appears as a PO counterparty | Returns raise an invoice in the PO list | Resolved by the business | Medium | Data team
D-046 | Purchase orders | Returned-to-supplier fields rarely filled | Kept as reported | Handled in the warehouse | Low | Data team
D-048 | Inventory | Stock report is a wide pivot, not a table | Loader unpivots to SKU x location and checks block headers | Handled in the warehouse | Medium | Data team
D-049 | Inventory | Report includes non-sellable items | Only Trading are SKUs | Resolved by the business | Medium | Data team
D-053 | Inventory | Product category blank in the stock report | Business rule (27 Oct 2026): category and sub-category come from the ERP item master (Product Master List) only; otherwise 'Uncategorised'. Schema 2.8: no trading stock is uncategorised. | Resolved by the business | Low | Data team
D-054 | Product master | Which SKUs are currently sold | Final Master is the list of current SKUs | Resolved by the business | High | Data team
D-055 | Product master | How current the master's status is | Updated whenever something changes | Resolved by the business | Medium | Data team
D-056 | Product master | Only Sheet1 is structured | Only Sheet1 loaded | Handled in the warehouse | Low | Data team
D-057 | WMS dispatch | CORRECTION: channel is in 'Site Location', not 'Customer' (earlier misread) | Corrected | Resolved by the business | Medium | Data team
D-058 | WMS dispatch | Which warehouse 'Warehouse' means | B2C only, all from Bagru | Resolved by the business | Medium | Data team
D-059 | WMS dispatch | Several SKUs in one cell with one combined quantity | Bridge table; per-SKU qty from the matching ERP invoice line, else left empty. Invoice match rate to be checked on the full export 2026-10-26 (schema 2.5-2.7): quantities taken from all ERP bills of the order, then two exact rules (ONE_EACH: quantity = number of SKUs; REMAINDER: the one unknown SKU gets the rest). Unallocated SKU lines 2,799 -> 4; the 4 left are 2 SKUs sharing 3 units and cannot be split from the data. | Handled in the warehouse | Medium | Data team
D-061 | WMS dispatch | Dates in month/day order | Date format declared per source | Handled in the warehouse | High | Data team
D-062 | WMS dispatch | Status values in mixed case | Standardised via ref.code_mapping | Handled in the warehouse | Low | Data team
D-063 | WMS dispatch | Placeholder customer contacts | PII not used in core | Handled in the warehouse | Low | Data team
D-064 | Quick commerce | Which Blinkit order statuses count as sold | Delivered = sold | Resolved by the business | Medium | Data team
D-065 | Quick commerce | No store id in the Blinkit sales export | Grain uses supply city in place of store | Handled in the warehouse | Low | Data team
D-066 | Quick commerce | Brand Metrics sheet is marketing data | Not loaded in this phase | Handled in the warehouse | Low | Data team
D-067 | Locations | Bagru warehouse naming across files | 08 Jaipur Branch = Bagru warehouse | Resolved by the business | Medium | Data team
D-068 | Locations | Head office location | HO is in Bagru | Resolved by the business | Low | Data team
D-070 | Inventory | The stock report has a 'Total' column that is the sum of all locations | Loader skips the Total block and uses it only to check the unpivot is complete | Handled in the warehouse | High | Data team
D-077 | Returns | One credit note can cover several goods receipts with different dates | Approved with Target Data Model v2 (1 Oct 2026): rule BR-023 | Resolved by the business | High | Data team
D-081 | Quick commerce | Instamart's 'Elle SKU' shows Excel's N/A lookup error where its lookup failed | Excel error values are treated as 'no SKU': rows go to Unknown and are counted | Handled in the warehouse | Low | Data team
D-082 | Returns | Return date column mixes real Excel dates and typed text | Loader stores Excel dates as ISO text and keeps typed text unchanged; staging parses both | Handled in the warehouse | Medium | Data team
D-084 | Scope | These exports carry no date of their own | Loader requires --as-of for every snapshot, state or master file. When saving these exports, put the full export date in the file name | Handled in the warehouse | Medium | Business (you)
D-085 | Inventory | 7 locations are selected in the report filter but have no column | Checked against all 19 stock reports (31 Mar 2025 - 15 Sep 2026): these 7 locations never had a column, i.e. never held stock. The ERP leaves empty locations out. Nothing to fix. | Handled in the warehouse | Medium | ERP team
D-086 | Inventory | Report ends with a grand-total row | Every location column must add up to its footer total, and every row to its Total column, or the whole file is rejected | Handled in the warehouse | Medium | Data team
D-087 | Product master | Sheet1 also contains a full copy of stock columns | Only the 5 product columns are loaded; the stock copy is ignored by design | Handled in the warehouse | Medium | Data team
D-088 | Quick commerce | Columns without a header | Dropped only after checking they are exactly a counter / only '--'; otherwise the file is rejected | Handled in the warehouse | Low | Data team
D-091 | Domestic sales | Classification by elimination is unsafe until the partner list is complete | Safety switch partner_list_complete = false: unlisted names stay UNCLASSIFIED until the business confirms the list is complete | Handled in the warehouse | High | Data team
D-093 | Stock transfers | Inward prefix 'STK' is shared by two receiving locations | Receiver taken from the linked outward document, not from the prefix | Handled in the warehouse | Medium | Data team
D-095 | Inventory | Stock 'as on 31-03-2025' not yet requested; rule BR-021 ('stock history cannot be re-pulled') is out of date for ERP locations | Stock reports for 31 Mar 2025 and every month-end to 31 Aug 2026 received (Oct 2026). Schema 2.11: 31 Mar 2025 is the opening stock (BR-033); month-end stock trend on the Stock dashboard. | Resolved by the business | High | ERP team
D-096 | Quick commerce | Blinkit and Instamart stock at 15-Sep-2026 cannot be re-fetched; only current-day stock is available | Accepted gap | Resolved by the business | Medium | Business (you)
D-097 | Quick commerce | Blinkit and Instamart sales history is a manually assembled workbook and cannot be re-fetched month by month | Decision: originals untouched; cleaned monthly files loaded; cleaning rules still to be confirmed in CLEANING_PLAN.md | Resolved by the business | High | Data team
D-099 | WMS dispatch | Dispatch file is .xlsm and Order Date is a real Excel date, but the draft WMS_DISPATCH contract expects text | Contract to be corrected against the real file before loading. Ask Operations to export future dispatch reports as CSV with ID columns as text 2026-10-22: contract verified against the full .xlsm export; dates read as real Excel date-times. | Handled in the warehouse | Medium | Business (you)
D-100 | Purchase orders | PO reports now have an extra column 'Document Remark' (38 columns; contract has 37) | Contract updated to 38 columns (schema 2.3); the meaning of Document Remark confirmed as rule BR-031 (schema 2.10). | Resolved by the business | Medium | Data team
D-101 | Product master | The first Final Master copy supplied lacked Sheet1 | Original file supplied | Resolved by the business | Medium | Business (you)
D-102 | General | Warehouse is to run on PostgreSQL 18; it was tested on PostgreSQL 16 | Confirmed: 78/78 schema tests (tests/test_schema.sql) and 63/63 pytest (49 loader, 6 seed, 8 transform; 0 skipped) on PostgreSQL 18.6 + Python 3.13.15, 2026-10-16 | Resolved by the business | Medium | Data team
D-104 | General | Python 3.13 used instead of the preferred 3.12 | Confirmed: 78/78 schema tests (tests/test_schema.sql) and 63/63 pytest (49 loader, 6 seed, 8 transform; 0 skipped) on PostgreSQL 18.6 + Python 3.13.15, 2026-10-16; requirements.txt pinned to the tested versions (commit 3ae9cea) | Resolved by the business | Medium | Data team
D-107 | General | A database named ellementry_dw already exists on the server; it belongs to the other model's prototype | Decision: keep ellementry_dw for the prototype evaluation; our warehouse = ellementry_warehouse | Resolved by the business | Medium | Business (you)
D-108 | Retail sales | Control total Rs 4,22,80,208.54 was mislabelled 'retail net sales' in earlier notes | Rs 4,22,80,208.54 is retail INVOICED sales excluding GST, before returns (sample period Apr-Sep 2026); net of returns dated Apr-Sep 2026 = Rs 3,69,30,320.14. Corrected in PRD-001 | Resolved by the business | Medium | Business (you)
D-109 | WMS dispatch | WMS Invoice No for marketplace orders (M25-, M26-, M44-...) never matches an ERP bill | Schema 2.5: link by Invoice No, else Extern Order No = bill order number, else Tracking No = bill AWB. Linked 24,893 -> 45,171 of 45,246. The M-series are the marketplaces' own invoice numbers (accounts may confirm; nothing depends on it now) | Handled in the warehouse | High | Data team
D-110 | Retail sales | ERP bill numbers restart every April (IN-1 exists in FY 25-26 and FY 26-27) | Schema 2.6: a bill is its number within a financial year (bill_fy_start in the line identity); returns link to the latest bill of that number on or before the return; reconcile.py uses the same key. Fixed 2026-10-26. Retail sales Apr 2025 - Sep 2026: Rs 13.66 Cr -> Rs 13.92 Cr; reconciles 28/28 | Handled in the warehouse | High | Data team
D-114 | WMS dispatch | Weight over 100 kg on 85 deliveries (max 265,650) | Schema 2.4: weights over 100 kg left out of v_fulfilment; WARN check shipment_weight_suspect | Handled in the warehouse | Low | Data team
D-115 | WMS dispatch | Site Location 'Ellementry International' maps to no channel | Ellementry International = B2C export (business, 27 Oct 2026). Schema 2.8: channel EXPORT_B2C, sales segment 'B2C export'. B2B exports go through Dileep. | Resolved by the business | Low | Business (you)
D-116 | Inventory | 103 trading SKUs have no MRP in any source (mostly discontinued) | Stock is valued at cost, not MRP (business, 27 Oct 2026). Schema 2.8: every trading SKU in stock has a cost in the ERP item master, so missing MRPs no longer affect stock value. | Resolved by the business | Medium | Business (you)
D-117 | Inventory | Active MRP for the same SKU differs between locations | Business rule (27 Oct 2026): where MRPs disagree the higher one is current (prices were raised; the lower MRP is old stock). Schema 2.8 takes the highest of stock report, latest invoice and item master. | Resolved by the business | Medium | Business (you)
D-119 | Inventory | Days of cover ignored stock leaving by transfer | Schema 2.4: cover = sellable / (sales + transfers out) per day over 30 days | Handled in the warehouse | Low | Data team
D-120 | Purchase orders | Over-received PO lines (pending quantity below zero) | Schema 2.4: v_purchase_order_lines.is_over_received; table on the Purchasing & transfers dashboard. Purchasing may want to review the 24 lines | Handled in the warehouse | Low | Data team
D-122 | Purchase orders | Goods receipts have no receiving location (gap G-025) | Business (27 Oct 2026): all goods receipts arrive at Bagru. Rule BR-032, schema 2.9: setting goods_receipt_location = BAGRU_WH places all 4,906 receipts. | Resolved by the business | Medium | Business (you)
D-123 | Inventory | Stock was valued at MRP; the company values stock at cost | Schema 2.8: unit cost from the ERP item master (COST); stock_value_cost on the Stock and Executive dashboards (Rs 3.86 Cr on 15 Sep 2026; Rs 14.80 Cr at MRP). | Resolved by the business | High | Business (you)

## Unsolved
ID | Area | Issue | Evidence | Why it matters | What is needed to solve it | Status | Priority | Owner
D-004 | Scope | Daily stock history is not available | The ERP can export the stock report for any single past day (month-ends 31 Mar 2025 - 31 Aug 2026 received Oct 2026), but not every day of the past 1.5 years | Stock can be shown by month-end but not by day or week; each unsaved day is lost | Month-end history is solved (19 stock days, schema 2.11). Still missing: daily stock. Save the ERP stock report every day from now into exports/_inbox/. | Open - business | High | Business (you)
D-007 | Scope | No Blinkit or Instamart invoices found in the ERP for Apr-Sep 2026 | No Kiranakart/Swiggy names in Domestic Sales; no QC channel in Retail Sales; yet Kiranakart appears in returns and Blinkit locations hold ERP stock | Quick-commerce revenue may be missing from ERP-based revenue | Quick commerce: focus is Instamart. How is stock supplied to Instamart (which invoice name or PO)? No invoices to any Swiggy / Instamart name were found in the ERP exports. Blinkit parked. | Open - business | High | Business (you)
D-019 | Domestic sales | CONTACTNAME mixes B2B, franchise, SIS, quick commerce, group exports and employees | 117 distinct accounts in the sample | Sale-or-return stock counted as final revenue | Rules confirmed. Billing names of franchise, SIS and QC partners still to be supplied (handled meanwhile: Separate partner types; B2B = final, franchise/SIS/QC = sale-or-return) | Open - business | High | Business (you)
D-023 | Domestic sales | Lines billed at normal price with a 99-100% discount (near-free) | 106 lines, 60 bills, Rs 63 total: Ayush Baid 42, Sundry Customer 22, Tanishq/Titan 14, others | Free units counted as sold: demand inflated for Stock AI; B2B sample units counted as B2B sales | Are these samples / free issues? (handled meanwhile: Proposed: flag lines with >=99% discount as 'free / sample issue' and exclude them from demand) | Open - business | High | Business (you)
D-038 | Stock transfers | Sending / receiving location only encoded in the document number prefix | Prefixes JPR/, THA/, HYD, BAG/, AMD ... ; no location column | Stock movements assigned to the wrong place when a new prefix appears | Add a branch / location column to transfer and return exports (handled meanwhile: Interim prefix-to-location table (ref.document_prefix_location)) | Open - ERP team | High | ERP team
D-080 | Inventory | Stock at sale-or-return partners has no opening balance | Blinkit consignment location shows -5,749 units: Kiranakart returned stock in the period that was invoiced to it before the data starts; Blinkit net sales -Rs 2.44 lakh for the same reason | Partner stock understated, even negative, on dashboards | Blinkit part parked (new seller arrangement; its consignment balance of -5,749 units is hidden from stock tiles). Franchise and SIS partners: stock each held on 1 Apr 2025 (gap G-028). | Open - business | High | Business (you)
D-089 | Returns | Shoppers Stop returns appear on two routes | PO report: 316 return-inward receipt lines (563 units); Domestic Sale Return: 68 credit-note lines (95 units); only 3 pairs match on SKU, quantity and date | If both record the same goods, the stock ledger counts the return twice | Are these two different return routes, or the same goods recorded twice? (handled meanwhile: No return-inward movements are created until the factory list arrives and this is answered) | Open - business | High | Business (you)
D-094 | Purchase orders | Export date of both PO files is unknown ('12.22' and '12.09' in the file names: time or date unclear) | File names end '12.22' and '12.09'; the sheets have no title row (header on row 1). PO Open Date in the 26-27 file runs to 24-Sep-2026. | The PO table keeps each line's latest status, so a wrong as-of date can roll a line's status back | Needs the business and the ERP team to state the export date (and time) of each PO file (handled meanwhile: Loader requires --as-of for ERP_PURCHASE_ORDER; PO loading is blocked until the date is given 2.4: meta.load_batch.as_of_is_assumed; the dashboard labels overdue days from the FY 25-26 export as 'export date assumed'.) | Open - business | High | Business (you)
D-005 | Scope | Blinkit return sheet (and Instamart's, if any) not received | Business confirmed returns are in a separate sheet | Quick-commerce returns missing; net sales overstated | Old Blinkit data set aside: a new seller arrangement with Blinkit starts (Oct 2026). Revisit with the new data. | Parked - Blinkit | Medium | Business (you)
D-006 | Scope | No sell-out data from franchise and SIS stores | Only sell-in invoices exist in the ERP | Stock AI reads stock that later comes back as demand | Business will work out how to extract it (handled meanwhile: Demand for these channels uses net sales after returns until sell-out arrives) | Open - business | Medium | Business (you)
D-024 | Domestic sales | 'Sundry Customer' is a catch-all account | 171 lines, 21 bills, Rs 4,960 taxable; products incl. cake stand, paper bags, tissue, gift cards | Default rule would treat it as an EMPLOYEE (not on business list) | What is Sundry Customer (walk-in / cash B2B / misc)? (handled meanwhile: Held as UNCLASSIFIED until answered) | Open - business | Medium | Business (you)
D-039 | Stock transfers | Outward stock never received | 31 of 622 outward documents wholly unreceived = 2,311 units (233 from Jun, 34 from May). CORRECTED total counting SKU lines, incl. partly received documents: 2,794 units in transit (built warehouse, verified independently) | Stock can disappear between locations | Schema 2.4 split the unreceived transfers: to Amazon FBA (receipts recorded by Amazon, not the ERP) vs own locations. Real exceptions: 1,441 units to own locations unreceived after 60 days; warehouse team to check (list on the Purchasing & transfers dashboard). | Open - ERP team | Medium | ERP team
D-047 | Purchase orders | CORRECTED: one GRN per PO line was assumed; part deliveries list several receipts in ONE cell | Found by the first transform run: 47 PO lines list 155 receipts in GRNNUM (e.g. 'JPR/GRN/199;305;89') with one date and one total quantity. The loader's uniqueness check could not catch it: it is one cell, not several rows | Per-receipt dates and quantities unknown; supplier lead time approximate for those lines | Still needed: a GRN register (one row per receipt with its own date and quantity). Without it, receipts land on one date per PO line, which makes month-to-month stock checks at Bagru swing (gap G-027). | Open - ERP team | Medium | ERP team
D-050 | Inventory | Same Blinkit stock reported by the ERP and by Blinkit | '27 Blinkit - Pune P2' (ERP) and 'Pune P2 - Feeder' (Blinkit) | Stock double-counted | Old Blinkit data set aside (new seller arrangement). Revisit with the new data. | Parked - Blinkit | Medium | Business (you)
D-051 | Inventory | Negative 'Net scheduled inventory' values | e.g. -92, -125 | Wrong stock at Blinkit | Being confirmed with Blinkit (handled meanwhile: Stored; excluded from all stock metrics) | Open - business | Medium | Business (you)
D-052 | Inventory | Amazon's own FBA inventory report not provided | FBA stock known only from the ERP | ERP and Amazon may disagree (see unreceived FBA transfers) | Can the Amazon FBA inventory report be exported? 2026-10-22: FBA stock on dashboards is the ERP's view only; transfers to FBA shown apart as 'receipt recorded by Amazon'. (handled meanwhile: FBA locations use ERP until an Amazon report is added) | Open - business | Medium | Business (you)
D-060 | WMS dispatch | Long numbers exported in scientific notation | Ext Manifest No '1.60396E+13' | Digits permanently lost; IDs don't match | Export IDs as text or the report as CSV (handled meanwhile: All IDs loaded as text) | Open - ERP team | Medium | ERP team
D-071 | Locations | 13 ERP locations hold zero stock, incl. 7 stores with no retail invoices | Stores: GK Store, Indiranagar, VR Mall, Infiniti Malad, SIB Bandra, Goa Anjuna, CG Road. Also DEPL Delhi / Lucknow / Mumbai PPOB and FBA BLR5, NAG1, DED5 | Closed locations clutter reports; stock appearing there later goes unnoticed | See 'Open questions' in Reference_Mappings_Draft_v1 (handled meanwhile: Proposed inactive; any stock or sale at an inactive location raises a warning) | Awaiting confirmation | Medium | Business (you)
D-072 | Locations | 'Dileep Essentials Pvt Ltd Bagru' is a different location from the Bagru warehouse | Uses transfer prefix BAG/ (2 documents); the Bagru warehouse uses JPR/ | Stock moved to / from it assigned to the wrong place | Is it '08 Bagru Popup'? (handled meanwhile: Left unmapped (goes to Unknown) until answered) | Open - business | Medium | Business (you)
D-073 | Locations | '08 Essential - DFAL' holds stock but its purpose is unknown | 688 units of 15 SKUs; transfer prefixes IS/DF and RC/DF | Stock counted as sellable when it may not be | What is DFAL, and is its stock sellable? (handled meanwhile: Proposed not sellable until confirmed) | Open - business | Medium | Business (you)
D-079 | Returns | A return 'reason' column exists but is never filled | Empty on all 5,924 rows | Return reasons unknown, though the ERP can hold them | Can the team start filling the reason when raising a credit note? Gap G-009 (handled meanwhile: Reason dimension ready; reasons load as soon as the field is filled) | Open - business | Medium | Business (you)
D-083 | Purchase orders | The PO export's real date is unknown | File name says '12_09' but it has 77 POs opened after 12-Sep, the latest on 24-Sep, and receipts to 24-Sep | PO state recorded against the wrong date; pending-PO view wrong | On what date was this PO report exported? Please note the export date for every future PO pull (handled meanwhile: Loader refuses a PO file whose as-of date is earlier than dates inside it 2.4: open PO lines from an export with an assumed date are labelled 'Overdue (export date assumed)' on the dashboard.) | Open - business | Medium | Business (you)
D-092 | Quick commerce | Two possible supply routes to Blinkit | Kiranakart (Blinkit) appears on domestic credit notes, while stock also reaches Blinkit feeder locations by ERP stock transfer | Blinkit stock split across two pools or counted twice | Old Blinkit data set aside (new seller arrangement). Revisit with the new data. | Parked - Blinkit | Medium | Business (you)
D-103 | Product master | Final Master as-of date not stated in the file | File metadata (docProps/core.xml): modified 2026-09-25T09:22:05Z, created 2026-02-06T11:10:55Z | Loader requires --as-of for PRODUCT_MASTER; a wrong date mis-times SKU status (Continued / Discontinued) | See 'How the warehouse handles it now' (handled meanwhile: as_of_date 2026-09-25 used in MANIFEST.tsv, assumed from file metadata) | Awaiting confirmation | Medium | Business (you)
D-105 | Returns | Amazon FBA customer returns report found; candidate source that may close gap G-009 (return reasons) | CSV, 12 columns incl. return-date, order-id, sku, asin, reason, detailed-disposition, customer-comments; 3,499 rows, return-date 2025-04-01 to 2026-09-14. G-009 (OPEN) names marketplace return reports as a way to fill return reasons | Return reasons stay unknown for Amazon returns; the free-text customer-comments column may hold personal data | See 'How the warehouse handles it now' (handled meanwhile: Not a registered source; stored in C:\ellementry_data\full\_UNREGISTERED\AMAZON_CUSTOMER_RETURNS\ and listed in MANIFEST.tsv as UNREGISTERED. Registering it needs a contract and a decision on customer-comments (exclude or restrict)) | Open - business | Medium | Business (you)
D-106 | Inventory | As-of dates of snapshot / master files assumed from file save times | Blinkit inventory: last saved 2026-09-25T10:08:47Z (15:38 IST); tests/sample_manifest.tsv said 2026-09-26. Instamart inventory: last saved 2026-09-26T06:03:19Z (11:33 IST), matches 2026-09-26. Final Master: last saved 2026-09-25T09:22:05Z; 2026-09-15 in sample_manifest was a placeholder (owner) | Loader requires --as-of; a wrong date places stock or SKU status on the wrong day | See 'How the warehouse handles it now' (handled meanwhile: MANIFEST.tsv as_of_date: Blinkit inventory 2026-09-25, Instamart inventory 2026-09-26, Final Master 2026-09-25 (stock files show stock at download time)) | Awaiting confirmation | Medium | Business (you)
D-112 | WMS dispatch | RTO is recorded only for website orders | 1,945 RTO deliveries, all website (7.9%); Amazon 3 of 9,482, others 0. Marketplace returns-to-origin are handled by the marketplace | An all-channel RTO rate (4.3%) understates the real rate and shows marketplaces as perfect | The WMS dispatch report is the OMS report (business, Oct 2026), so it has nothing more. Marketplace RTO must come from seller-panel return / RTO reports (Amazon, Myntra, Tata Cliq, Nykaa). | Open - business | Medium | Business (you)
D-113 | WMS dispatch | No delivery dates for Nykaa, FNP and Flipkart | Nykaa 2,701 of 2,784 stuck at SHIPPED; FNP and Flipkart all | Delivery time and late-delivery measures wrong for these channels | 4,778 deliveries stuck at 'Shipped' (Nykaa 2,701, website 951, Amazon 688, Tata Cliq 208, others); 2,932 with no delivery date at all. Need: courier exports by AWB (Delhivery / Shiprocket portals) for the website, seller-panel order reports for marketplaces. | Open - business | Medium | Business (you)
D-124 | Inventory | Stock moves at Bagru with no document in the exports | Month-by-month check (schema 2.11, mart.v_stock_movement_check): over 1 Apr 2025 - 15 Sep 2026, 71,350 units arrived at Bagru and 55,188 left with no sale, transfer, return or PO receipt. E.g. Gaudeep gold diya set of 11: 9,868 arrived with no receipt; gift boxes and paper bags left with no document. List: reports/bagru_unexplained_stock.csv | Stock between month-ends cannot be rebuilt exactly; purchases without a PO, gift-set assembly and packaging use are invisible | An item-wise stock ledger (or GRN register incl. non-PO purchases, assembly / kitting register, stock adjustment / consumption register) for Bagru, 1 Apr 2025 - 15 Sep 2026. The 'Item Wise Pending Purchase Order Tracking' file received 30 Oct 2026 was empty (01/04/2024 - 31/03/2025) and is PO-only. | Open - ERP team | Medium | ERP team
D-125 | Quick commerce | No Instamart inventory, and the seller portal shows only today's stock | Instamart seller login gives the current day's inventory only; no official history download or API found | No Instamart stock or cover on the dashboards | 1) Download the inventory every day from now into exports/_inbox/ (loader ready). 2) Ask the Instamart category manager for a historical inventory dump. 3) Tell us how Instamart is supplied, so history can be rebuilt from shipments and the daily sell-out we already have. | Open - business | Medium | Business (you)
D-015 | Retail sales | Two Nykaa names: 'Nykaa Fashion' (900 lines) and 'Nykaa' (34 lines) | Payment modes 'Prepaid - Nykaa Fashion' and 'Prepaid - Nykaa' | Nykaa split across two channels | See 'How the warehouse handles it now' (handled meanwhile: Proposed: one channel 'Nykaa' with the two names kept as sub-channels) | Awaiting confirmation | Low | Business (you)
D-027 | Domestic sales | Direct export rows to Singapore, although exports are said to go through Dileep | 2 lines to 'Hindustan Exports', Rs 1 each | Unclear classification | Are these samples to an exporter? (handled meanwhile: Held as EXPORT_CUSTOMER; Rs 1 lines also fall under the near-free issue) | Open - business | Low | Business (you)
D-036 | Returns | Domestic returns have no clear link to the original invoice | BILLNUM here is the credit note; RTNFROMCUST is the goods receipt | Cannot compute return rate per original B2B invoice | Is the original invoice number stored anywhere in this report? (handled meanwhile: Original bill kept nullable) | Open - ERP team | Low | ERP team
D-069 | General | Currency and timezone never explicitly confirmed | All data appears Indian (INR, IST) | Wrong if any foreign-currency data exists | See 'How the warehouse handles it now' (handled meanwhile: INR and IST stored as settings) | Awaiting confirmation | Low | Business (you)
D-074 | Locations | Jaipur Meeraki holds stock but has no retail invoices | 145 units; no Retail Sales rows Apr-Sep 2026 | Store type unclear (own / SIS / franchise) | What kind of store is Meeraki? (handled meanwhile: Proposed own store) | Open - business | Low | Business (you)
D-075 | Locations | Two store names don't match any ERP location | 'Dileep Essentials Pvt Ltd Jaipur Store' (7 returns) and 'Dileep Essentials Pvt Ltd Lucknow' | Returns received at an unknown location | Which locations are these? (handled meanwhile: Left unmapped until answered) | Open - business | Low | Business (you)
D-076 | Retail sales | Channels seen only in last year's returns | 'Flipkart Website', 'Ellementry International', and Blinkit Mumbai / Pune contacts | Channel list incomplete for FY25-26 | Which channel is 'Ellementry International'? (handled meanwhile: Flipkart and Blinkit mapped (proposed); Ellementry International left unmapped) | Open - business | Low | Business (you)
D-078 | Returns | Receipt date list shorter than the receipt list on some credit notes | e.g. 3 receipts with 2 dates; 100 receipts in the sample cannot be paired with a date | Wrong receipt dates if paired by position | Why does the ERP drop a date when several receipts share one credit note? (handled meanwhile: Unpaired receipts left out of the receipts bridge; the return uses only the dates given) | Open - ERP team | Low | ERP team
D-090 | Domestic sales | 'DILEEP ESSENTIALS INC' appears as a return counterparty | 1 row | Unclear whether it is a group export entity | What is Dileep Essentials Inc? (handled meanwhile: Listed as UNCLASSIFIED so it is never classified by elimination) | Open - business | Low | Business (you)
D-098 | Domestic sales | DOCID is a 19-digit number stored as a number, so its last digits cannot be exact | All 25,863 DOCID values (20,612 + 5,251) are 19 digits and stored as floating-point numbers (about 15-16 digits are exact) | DOCID cannot be used as a reliable key | Ask the ERP team for a text export when convenient (handled meanwhile: DOCID is kept in the raw layer only; not used by the warehouse) | Open - ERP team | Low | ERP team
D-111 | WMS dispatch | 39 courier spellings for about 10 companies (Delhivery 13 ways, Bluedart 6, Ekart 4; codes ATS, XC, DL, DE_*, BD_*, EK_*) | Transporter / Ext Transporter Name columns | Courier comparisons split one company across many rows | Confirm the courier codes: ATS = Amazon Shipping, XC = Xpressbees, DL / DLV / DE_* = Delhivery, BD_* = Blue Dart, EK_* = Ekart (all mapped from data evidence, unconfirmed). | Awaiting confirmation | Low | Business (you)
D-118 | Inventory | Negative stock in the ERP report | Jaipur C-Scheme -10, Bangalore 7 -2 units | Stock totals slightly off; signals booking errors | An ERP glitch the ERP team cannot fix yet; the business is looking at it. 15 Sep 2026 report, sheet ChannelwiseStock: row 1602 coll003-1 Gift card at 08 Jaipur - C-Scheme -10; row 1673 GSTEA1905 at 29 FBA WH - Bangalore 7 -1; row 3030 SWETA2778 at 29 FBA WH - Bangalore 7 -1 (32 negative rows across the 19 reports). Decide: treat as 0, exclude, or show as reported (current). | Open - business | Low | ERP team
D-121 | Purchase orders | PO lines with no due date | 223 lines (3 still open) | Cannot be judged overdue | Fill due dates in the ERP (handled meanwhile: Schema 2.4: due_status 'No due date' on open PO lines) | Open - ERP team | Low | ERP team